## Comm Mgt Plan Template
Communications plan template for project: AHI Real-Time Marketing Analytics App
Communications item forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format medium (How) (Where) | Purpose (Why)
Weekly Project Status Meeting | Cary Manning | All key stakeholders | Weekly – Thursdays 10:00 AM | Video call (Teams) | Review progress, issues, risks, and deliverables
Sponsor 1:1 Meeting | Cary Manning | Mary Smithers (Sponsor) | Weekly – Wednesdays 9:00 AM | Mary's office | Provide project update, escalate issues, review help needed
Status Report (Written) | Cary Manning | All stakeholders | Weekly – Fridays by 12:00 PM | Email + SharePoint | Provide summary of status, risks, milestones
Change Control Board (CCB) Meeting | Cary Manning | CCB Members | Biweekly – Mondays 11:00 AM | Teams Meeting | Review change requests, approve or reject changes
IT and QA Sync | Keiko Tanaka | Priya Service (IT), Dev Team | Biweekly – Tuesdays 3:00 PM | Teams | Review dev quality, test progress, and open issues
Vendor Coordination Meeting | Cary Manning | External App Vendor | Weekly – Mondays 2:00 PM | Teams or vendor platform | Ensure alignment on deliverables and timelines
Training Readiness Review | Keiko Tanaka | Internal Trainers | One-time – Oct 1, 2:00 PM | Conference Room | Finalize training materials and delivery schedule
Risk Review Session | Cary Manning | Priya, Ram, Mary | Monthly – Last Friday 2:00 PM | Teams | Identify, review, and update project risks
Post-Launch Feedback Review | Keiko Tanaka | Ram Samuels, Focus Group | One-time – Nov 15, 10:00 AM | Teams/Focus Room | Gather and assess beta test and live app feedback
Version: 01 |  |  | Date: 20 Apr 20XX