## Template
High-Level Budget: Resource Breakdown Structure Project Name: AHI Real-Time Marketing Analytics App Date: 19 Apr 20XX
WBS identifier # | Work package | Internal personal required | External personnel required | Venue costs | Materials required | Supplies required | Equipment required | Comments | Total direct costs
1.1.1 | Define app objectives and success | 1000 | [5 empty] | Business alignment | 1000
1.1.2 | Identify stakeholder needs | 1000 | [5 empty] | Stakeholder analysis | 1000
1.1.3 | Create schedule and milestones | 1000 | [5 empty] | PM planning | 1000
1.1.4 | Budget and resource planning | 1000 | [5 empty] | Finance team input | 1000
1.1.5 | Define product backlog themes | 1000 | [5 empty] | Initial backlog development | 1000
1.1.6 | Agile execution model setup | 1000 | [5 empty] | Sprint framework setup | 1000
2.1.1 | Set up development and test environments | 5000 | 15000 | 15000 |  |  |  | IT systems and storage setup | 35000
2.1.2 | Build backend systems (predictive) | 8000 |  |  |  |  | 40000 | Backend architecture and APIs | 48000
2.1.3 | Develop user-facing features (agile) | 12000 |  |  |  |  | 60000 | UI/UX, ordering, customer engagement | 72000
2.1.4 | Integrate analytics and data feeds | 5000 |  |  |  | 5000 | 15000 | Real-time analytics + market/competitor data | 25000
2.1.5 | Test app (unit, UAT, beta testing) | 5000 |  |  |  |  | 10000 | Quality assurance with internal and user testing | 15000
2.1.6 | Launch app and train users | 5000 |  |  | 20000 |  | 9000 | Deployment, onboarding, and support | 34000
3.1.1 | Monitor app performance | 1500 | [5 empty] | Post-launch monitoring by PMO and IT | 1500
3.1.2 | Collect feedback and metrics | 1000 | [5 empty] | Customer focus group feedback | 1000
3.1.3 | Analyze ROI and outcomes | 1000 | [5 empty] | Finance review and analysis | 1000
3.1.4 | Conduct lessons learned | 500 | [5 empty] | Team session and documentation | 500
3.1.5 | Finalize documentation and closeout | 1000 | [5 empty] | Reports, archiving, and closeout activities | 1000
TOTAL cOSTS |  | 51000 | 15000 | 15000 | 20000 | 5000 | 134000 | 0 | 240000
Contingency requirements (10%) | [8 empty] | 24000
Personnel cost requirements
Rate | Name | Hours | Costs
$100/hr | Cary Manning (PM) | 63 hrs | 6300
$90/hr | Cal Hamer (Product Owner) | 62 hrs | 5580
$85/hr | Priya Service (IT Lead) | 69 hrs | 5865
$80/hr | Keiko Tanaka (Marketing) | 69 hrs | 5520
$80/hr | Jose Garcia (Marketing) | 69 hrs | 5520
$85/hr | QA/Test Lead | 55 hrs | 4675
$70/hr | Training Lead | 56 hrs | 3920
$100/hr | Ram Samuels (SME) | 38 hrs | 3800
$75/hr | Dev Lead (Backend) | 70 hrs | 5250
$75/hr | Dev Lead (Frontend) | 60 hrs | 4570
TOTAL |  |  | 51000