## Product Backlog
Product Backlog for Project: AHI Real-Time Marketing Analytics App
User Story Identifier | Priority | Category | Team | Role | Need | Value | Acceptance 1 | Acceptance 2 | Acceptance 3 | Acceptance 4 | Story Points | Comments
0001 | 3 | Leadership | Analytics | AHI Executive | Understand customer segments and market trends | Make informed strategic decisions | Reports available on demand | Export to PDF/Excel is available | Filter by geography and behavior | Data updates daily from real-time feeds | 5 | Sprint 2
0002 | 1 | Marketing | Analytics | Marketing Analyst | Track customer interest and views in real time | Adjust campaigns and promotions quickly | Real-time dashboard | Filter by product/region | Visual charts available | Export to PPT/Excel | 8 | Sprint 1
0003 | 2 | Finance | Backend/Finance | Finance Officer | Secure invoicing and financial forecasting | Manage revenue and sales planning | Encrypted invoicing | 3-6 month sales forecast reports | Exportable in Excel | Access-controlled | 5 | Sprint 1
0004 | 4 | IT | Infrastructure | IT Administrator | App must integrate with infrastructure | Ensure stability and security | Passes compatibility checklist | Compatible with firewall and antivirus | Logs integration errors automatically | Meets IT storage requirements for data logs | 3 | Sprint 1
0005 | 5 | Customer | Frontend | AHI Customer | Secure, simple product access and order confirmation | Shop confidently and quickly | Pages load in 3 seconds | Secured checkout and support credit card and paypal | Order confirmation within 2 minutes | View order history after login | 3 | Sprint 3
Total Story Points: 24

## Product Backlog Example
Product Backlog for Project
User Story Identifier | Priority | Category | Team | Role | Need | Value | Acceptance 1 | Acceptance 2 | Acceptance 3 | Acceptance 4 | Acceptance 5 | Story Points | Comments
0001 | 1 | Customer | App Dev 1 | As a Coffee Shop Customer | I need easy access to order | To save time and reduce waiting | 1. Easy access to menu | 2. Pricing for all options | 3. Secure monetary transaction | 4. Order Confirmation |  | 5 | Sprint 1
0002 | 2 | Employee | App Dev 1 | As a store employee | I need real-time access to orders | So I can prepare in a timely manner | 1. Order information clearly displayed | 2. Customer's name | 3. Desired pick-up time | 4. Special instructions | 5. Label generation | 2 | Sprint 1

## Story Points
1 Story Point | 2 Story Points | 3 Story Points | 5 Story Points | 8 Story Points
Less Complex More Complex
User Story 1
User Story 2
User Story 3
User Story 4
User Story 5

## Story Points Solution
1 Story Point | 2 Story Points | 3 Story Points | 5 Story Points | 8 Story Points
Total Story Points: 1 + 2 + 3 + 3 + 5 = 14
Less Complex More Complex
User Story 1
User Story 2
User Story 3
User Story 4
User Story 5