## Plan Phase
6. Plan Agile execution model and sprint cadence
3 days
5. Define Product Backlog themes
5 days
3. Develop Schedule and budget
5 days
4. Develop support plan
3 days
2. Identify stakeholders rquirements
2 days
1. Define app scope and sucess criteria
3 days
Start
End
Buffer
3 days
Project: AHI Real-Time Marketing Analytics App - Plan Phase
Critical Path = 21 days
6. Prepare training materials
5 days
5.Conduct testing
10 days
2. Build Backend Systems
15 days
3. Integrate analytics
10 days
4. Scrum activity
35 days
1. Set up environments
5 days
Start execution
Ready for close phase
Buffer
5 days
Project: AHI Real-Time Marketing Analytics App - Execute Phase
Critical Path = 70 days
7. Launch app and train users
10 days
4. Conduct Lessons Leraned
3 days
5.Analyze ROI and outcome
3 days
2. Collect Feedback
5 days
1. Monitor performance
5 days
Start Close phase
Close out
Buffer
5 days
Project: AHI Real-Time Marketing Analytics App - Close Phase
Critical Path = 25 days
5. Finalize documentation
4 days