## Quality Mgt Plan Template
Quality management plan for project: AHI Real-Time Marketing Analytics App Version: 1, Date 20 Apr 20xx
Part I: Project objectives (reference project charter)
1. Ensure the app meets all business and functional requirements from the product backlog.
2. Deliver a defect-free product at time of launch.
3. Ensure the app performs reliably and securely under expected loads.
4. Provide a user experience that aligns with AHI’s brand and customer expectations.
5. Validate that analytics and market data functions provide accurate, timely outputs.
6. Maintain effective collaboration between internal teams and the external vendor.
7. Ensure quality is built into every phase — from planning through deployment.
Part II: Project quality team (Project Manager, QA, QC, SME)
Name | Role | R (Responsible) | A (Accountable) | C (Consult) | I (Inform)
Cary Manning | Project Manager | X | X |  | X
Keiko Tanaka | QA/QC Lead | X | X
Priya Service | IT SME |  |  | X | X
Ram Samuels | Marketing SME |  |  | X | X
External Vendor | App Development Team | X
Mary Smithers | Sponsor |  |  | X | X
Quality assurance activities (quality audits) |  |  | Quality control activities (quality inpections)
Review requirements and backlog for clarity and testability |  |  | Verify final App design
Audit design process |  |  | Verify built features against user stories and acceptance criteria
Audit development process - code reviews |  |  | Verify App V1
Validate that test plans align with quality objectives |  |  | Verify Beta testing and feedback
Audit final launch planning |  |  | Verify final launch checklist
Audit feedback collection |  |  | Verify feedback receipt and findings