## Risk Register Template
Project: AHI Real-Time Marketing Analytics App Date: 20 Apr 20xx
# | Cause (condition/situation) | Event | Impact | Risk owner | Category | Probability risk rating | Impact risk rating | Risk score | Trigger | Response
1 | Hard to find IT staff | Can’t hire support in time | Delays in development | Priya Service | Threat | 4 | 4 | 16 | Roles unfilled 2+ weeks | Speed up hiring, ask sponsor help
2 | Low beta test turnout | Not enough user feedback | Missed bugs or bad user experience | Keiko Tanaka | Threat | 3 | 4 | 12 | Low test responses | Remind testers, give small rewards
3 | Vendor not aligned | Late or incomplete deliverables | Project falls behind | Cary Manning | Threat | 3 | 4 | 12 | Missed vendor milestone | Weekly check-ins, shared task list
4 | Strong team collaboration | Fast problem solving | Fewer delays, better quality | Project Team | Opportunity | 3 | 4 | -12 | Team hits early milestones | Keep communication strong
5 | No change control in place | Extra features added without review | Scope creep, delays | Cal Hamer | Threat | 2 | 4 | 8 | Backlog changed without CCB | Set up CCB and review process early
6 | Support team not trained | Users struggle after launch | More tickets, unhappy users | Priya Service | Threat | 3 | 4 | 12 | Feedback shows confusion | Train helpdesk, have launch-day support
7 | Training well received | Staff ready on day one | Smooth rollout | Keiko Tanaka | Opportunity | 3 | 3 | -9 | Positive UAT comments | Keep training simple and clear
Total Risk Score | [7 empty] | 29 | Risk Exposure
|  | Probability risk rating |  | Impact risk rating
|  | 5: High |  | 5: High
|  | 4: High to moderate |  | 4: High to moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to low |  | 2: Moderate to low
|  | 1: Low |  | 1: Low