## Blank
Sprint Backlog for Project: AHI Real-Time Marketing Analytics App - Sprint 1
Story ID | Resource | Story/Task | Time Required | Time Remaining
0002 Marketing needs 1 | Lead: Keiko Tanaka | User Story: Real-time customer interest tracking | 40
| Keiko Tanaka | Task 1: Define interest metrics and design dashboard layout | 11
| Dev Team | Task 2: Develop data feed integration | 10
| Dev Team | Task 3: Add filters for region/product | 8
| Keiko Tanaka | Task 4: Create visual reports | 6
| QA Team | Task 5: Test dashboard performance | 5
0003 Finance needs 1 | Lead: Oscar Money | User Story: Secure invoicing and sales forecasting | 30
| Oscar Money | Task 1: Set up secure invoicing system | 6
| Dev Team | Task 2: Develop user access control | 5
| Dev Team | Task 3: Build forecast calculation logic | 9
| Oscar Money | Task 4: Format exportable reports | 5
| QA Team | Task 5: User acceptance testing | 5
0004 IT needs 1 | Lead: Priya Service | User Story: IT compatibility and infrastructure checks | 22
| Priya Service | Task 1: Run compatibility checks | 4
| IT Team | Task 2: Test firewall and antivirus | 5
| Dev Team | Task 3: Implement error logging | 6
| Priya Service | Task 4: Generate system reports | 4
| Priya Service | Task 5: Review with IT team | 3
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
Total Sprint Hours |  |  | 92 | 0

## Example
Sprint Backlog for Project: Coffee Shop App
Story ID | Resource | Story/Task | Time Required (Hours) | Time Remaining (Hours)
0001 Customer Needs 1 | Lead: Ram | User Story: Easy Access to Orders | 77
| Marvin | Task 1: Develop visible drop-down menu | 20
| Marvin | Task 2: List easy to view pricing for all menu options | 15
| Don | Task 3: Develop secure payment transaction feature | 30
| Mona | Task 4: Develop order confirmation acknowledgement function | 12
Task 5
0002 Employee Needs 1 | Lead: Sally | User Story: Real-Time Access to Orders | 30
| Kyoko | Task 1: Develop visual order confirmation screen | 10
| Priya | Task 2: Program capability to see customer's name | 5
| Priya | Task 3: Clearly display order pick-up time | 5
| Harold | Task 4: List any applicable special instructions | 5
| Harold | Task 5: Automatically generate label when order is complete | 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
Total Sprint Hours |  |  | 107 | 0