## Template
|  | 1.0 AHI App Development Project |  | Level 1 Project level
1.1 Plan Project | 2.1 Execute Project |  | 3.1 Close Project | Level 2 Phase level
1.1.1 Define scope, goals, and constraints | 2.1.1 Set up development and testing environments |  | 3.1.1 Monitor app performance and stability | Level 3 Work package level
1.1.2 Identify stakeholders and roles | 2.1.2 Build backend systems and integrate APIs (predictive) |  | 3.1.2 Collect user feedback and satisfaction data
1.1.3 Develop project schedule and milestones | 2.1.3 Develop user-facing features via sprints (adaptive) |  | 3.1.3 Analyze ROI and project outcomes
1.1.4 Create budget and resource plan | 2.1.4 Conduct system, UAT, and beta testing |  | 3.1.4 Conduct lessons learned session
1.1.5 Develop risk and communication plans | 2.1.5 Launch app and deliver training |  | 3.1.5 Finalize closeout documentation and release resources
1.1.6 Draft initial product backlog and define agile setup | 2.1.6 Monitor app performance post-launch